## Sheet1
S No | Process | Sub process | Business Requirement | Reported Date | Initiated by | Status | Pending at
1 | PO | Briquette | Briquette:Newly encountered that frieght is coming for briquettes which was not informed earlier, yet to be informed to conrncerned Freight amount should be captured and BOT also need to change accordingly. | 2019-10-03 | Ayyappa | Open | Algonox
2 | PO | Transport Cases | Transported cases: As informed earlier, We encountered many new scenarios which were neither informed to us nor we got such scenarios in UAT 1. If invoice comes with GST tax code should be entered accordingly (70 or 72); without GST enter HY. 2. If comes under SEZ replace tax code with 00 3. Deduct TDS for all transport cases, if WHT is deactivated, move to genpact. 4. Invoices with ST charges, deduct TDS only on TDS base amount provided by CM,Invoice also should account without including the ST charges 5. If Transport case come with SEN (i.e. Service Invoice) treat as simple service. 6. In Miro we have to verify the vendor code with CM, and if any mismatch replace with vendor code provided in CM. | 2019-09-03 | Ayyappa | Completed and tested except simulation part(since skipping of validating CSGST & IGST is included recently) | Algonox
3 | PO | CHA | CHA:Completed the development acc to initial requirement but as ACE /CM input was not clear after disscussing with Ram we kept on hold. (If no new scenarios has to be handled then our initial code will work) | 2019-09-03 | Ayyappa | Started Development | Algonox
4 | PO | All scenarios may come under SEZ, which requires code changes. | Tax code logic for SEZ Services: All scenarios (Briquette,coal, freight,CHA for SEZ plants) may come under SEZ, which requires code changes. All processes xamls need to be changed and tested. Separate doc type field need to create in BOT properties for SEZ | 2019-10-04 | Ayyappa | Open | Algonox
5 | PO | TDS calculation logic needs to be changed | 194 J Logic has to be changed(for all the categories where TDS should be deducted) | 2019-10-14 | Sirisha | Dropped | GBS
6 | NON PO | All Non PO scenarios | HSN/SAC is not defined for country IN error: Previously BOT used to enter HSN number in HSN/SAC Field, now need to enter in assignment Field for all invoices. | 2019-10-10 | Ayyappa | Completed | Algonox
7 | NON PO | All Non PO scenarios | Posting period is not open error: We are moving to Genpact queue when this error occurs, now need to enter current date and close the case. | 2019-10-10 | Ayyappa | Completed | Algonox
8 | NON PO | Cab GST calculation | GST Calculation logic needs to be changed | 2019-10-11 | Sirisha | Completed | Alganox
9 | NON PO | Bus GST Calculation(PO and NON PO) | Approach still needs to be finalized how Datacap will give input to BOT (whether it’s a Bus invoice or no)t, once confirmed than only we can estimate efforts. | 2019-10-11 | Sirisha | Open | Joint
10 | NON PO | Cab invoices | New field is creating for cab invoices: BOT should capture that text in the SAP fi document text field for both line items | 2019-10-17 | Sirisha | Dropped | Joint
11 | NON PO | Employee reimbursements | No HIT fould cases | 2019-10-17 | Ayyappa | Completed | GBS
12 | PO | PO - service and SEZ service | If TDS base Amount is zero for service category invoices then those should move to manual Que,BOT should check if it is more than Zero then only it should process | 2019-10-17 | Ayyappa | Dropped | Algonox
13 | PO | TDS | If master consists of one tds code system should pick automatically | 2019-10-18 |  | Open | GBS
14 | NON PO | Revenue Expenses | New TDS logic | 2019-10-30 | Ram | Completed | Algonox
15 | PO | Freight | Picking up respective quantity for respective freight line item | 2019-11-04 | Ram | Open | Algonox
16 | PO | Transport Cases | Considering Taxcodes depending on various CM inputs | 2019-11-04 | Ram | Open | Algonox
17 | NON PO | Revenue Expenses | No Taxcode exists for VENDOR popup:---If exists replace with vendorcode | 2019-11-04 | Ayyappa | Open | Algonox